## Sheet1
| Risk | Severity | Probability
R1 | R1: Software ill defined | 3 | 7
R2: Time Estimation | R2: Inaccurate Time Estimations | 6 | 8
R3 | R3: Requirements ill defined | 4 | 5
R4 | R4: Lack of knowledge | 3 | 8
R5 | R5: Architecture & Design misplanning | 5 | 5
R6 | R6: Team conflicts | 6 | 3
R7 | R7: Work Organization due to COVID-19 pandemics | 2 | 6
R8 | R8: Illness of a team member | 4 | 6
R9 | R9: Temporal unavailability (1-3 weeks) except for illness of a team member | 4 | 3
R10 | R10: Permanent unavailability (>4 weeks) of a team member | 7 | 1
R11 | R11: Lack of ownership | 4 | 4
R12 | R12: Poor Code Quality | 7 | 5
R13 | R13: Poor Productivity | 6 | 5
R14: Advanced Feature | R14: Advanced Feature | 7 | 7
R15 | R15: Technical breakdown | 3 | 4