## Timeline
| 2020-10-05 |  | 12.10.2020 (KW-42) |  |  | 19.10.2020 (KW-43) |  |  |  |  | 26.10.2020 (KW-44) |  |  |  | 02.11.2020 (KW-44) |  |  |  | 09.11.2020 (KW-45) |  | 16.11.2020 (KW-46) |  |  | 23.11.2020 (KW-47) |  |  | 30.11.2020 (KW-48) |  |  |  | 07.12.2020 (KW-49) |  |  |  | 14.12.2020 (KW-50) |  | 21.12.2020 (KW-41) |  |  | 28.12.2020 (KW-52) |  |  | 04.01.2021 (KW-1) |  |  |  | 11.01.2021 (KW-2) |  |  | 18.01.2021 (KW-3) |  |  |  | 25.01.2021 (KW-4) |  |  | 01.02.2021 (KW-5) |  |  | Total
Appointments | [6 empty] | PP | [8 empty] | MR1 | [7 empty] | IR1 | [7 empty] | MR2 | [14 empty] | IR2 | [6 empty] | MR3
Sprint Planning | [7 empty] | PP Post |  | Template Prep + Doc | [6 empty] | MR1 Post |  | Sprint 1: 65% | [10 empty] | R |  |  | MR2 Post |  | Sprint 2: 35% |  |  | RED |  |  | Sprint 2 |  |  |  |  | R |  | RED |  |  | Buffer
3rd party exams
G | [49 empty] | AIC/FMI | MNSA |  |  | HPC
L | [11 empty] | UE |  |  |  | Pr | Pr |  |  |  | UE |  |  |  | UE | [9 empty] | UE | [8 empty] | UE | [5 empty] | UE
M | [11 empty] | AKH | [9 empty] | DF Midterm | [12 empty] | DF Final | [14 empty] | AIC/FMI | MNSA
N | [21 empty] | DF Midterm | [12 empty] | DF Final | [14 empty] | AIC/FMI | MNSA | IBM
S | [16 empty] | Pr | [10 empty] | Pr | [21 empty] | AIC/FMI | Pr |  |  | Pr | Pr |  |  | Pr | Pr
T | [11 empty] | GWG | [15 empty] | GWG | [18 empty] | IL |  |  | GWG | [8 empty] | EWBS
Deliverables | [17 empty] | Scrum Poker
|  |  |  | Project Proposal | 20 | [7 empty] | Architecture | 4 | [14 empty] | See dog in AR (can be hardcoded) | 150 | [14 empty] | Full AR (load 3D model from database) | 120
[13 empty] | Test plan | 4 | [14 empty] | View, add, remove animals | 80 | [14 empty] | Watchlist | 50
[13 empty] | CI Pipeline | 10 | [14 empty] | Filter animals | 70 | [14 empty] | Recommendations | 50
[13 empty] | Design (Class Diagram) | 10 | [14 empty] | User control | 70 | [14 empty] | Swipe Feature | 20
[13 empty] | Functional Requirements (User Stories) | 6
[13 empty] | Non-functional Requirements (User Stories) | 6
[13 empty] | Template setup | 8
[13 empty] | Review + Release | 20
[9 empty] | Code Style Guides | 4
Deliverables est. total hours |  |  |  |  | 20 |  |  |  |  | 4 |  |  |  | 68 | [15 empty] | 370 | [15 empty] | 240
Meetings est. total hours |  | 24 |  |  | 20 |  |  |  |  | 12 |  |  |  | 12 |  |  |  | 12 |  | 12 |  |  | 12 |  |  | 12 |  |  |  | 12 |  |  |  | 12 |  | 12 |  |  | 0 |  |  | 0 |  |  |  | 12
total available h/week |  | 30 |  |  | 60 |  |  |  |  | 60 |  |  |  | 90 |  |  |  | 60 |  | 90 |  |  | 90 |  |  | 90 |  |  |  | 90 |  |  |  | 30 |  | 90 |  |  | 0 |  |  | 60 |  |  |  | 90 |  |  | 0 |  |  |  | 0 |  |  | 6 |  |  |  | 936
target h/week/p.P. |  | 5 |  |  | 10 |  |  |  |  | 10 |  |  |  | 15 |  |  |  | 10 |  | 15 |  |  | 15 |  |  | 15 |  |  |  | 15 |  |  |  | 5 |  | 15 |  |  | 0 |  |  | 10 |  |  |  | 15 |  |  | 0 |  |  |  | 0 |  |  | 1 |  |  |  | 156
G |  | 3.5 | [57 empty] | 3.5
L |  | 3.5 | [57 empty] | 3.5
M |  | 3.5 | [57 empty] | 3.5
N |  | 3.5 | [57 empty] | 3.5
S |  | 3.5 | [57 empty] | 3.5
T |  | 3.5 | [57 empty] | 3.5

## Estimation
| Tutorial | Implementation |  |  |  | Quality/Testing | Documents | Meetings | Total | p.P
|  | Mobile | Web | Back | Tot
Android Template | 30 | 3 |  |  | 3 |  |  |  | 33 | 5.5
Web Angular Template |  |  | 3 |  | 3 |  |  |  | 3 | 0.5
Backend Template |  |  |  | 2 | 2 |  |  |  | 2 | 0.33333
See dog in AR (hardcoded) | 30 | 90 |  |  | 90 | 30 |  |  | 150 | 25
Full AR (load 3D model from database) | 10 | 40 |  | 30 | 70 | 20 |  |  | 100 | 16.6667
View, add, remove animals |  | 20 | 20 | 20 | 60 | 20 |  |  | 80 | 13.3333
Filter animals |  | 20 | 20 | 15 | 55 | 15 |  |  | 70 | 11.6667
User roles + administration |  | 20 | 20 | 15 | 55 | 15 |  |  | 70 | 11.6667
Watchlist |  | 15 | 15 | 10 | 40 | 10 |  |  | 50 | 8.3333
Recommendation |  | 15 | 15 | 10 | 40 | 10 |  |  | 50 | 8.3333
Swipe Feature | 5 |  |  | 10 | 10 | 5 |  |  | 20 | 3.3333
CI Pipeline | [5 empty] | 10 | 4 |  | 14 | 2.3333
Test plan | [6 empty] | 6 |  | 6 | 1
Architecture | [6 empty] | 6 |  | 6 | 1
Design | [6 empty] | 6 |  | 6 | 1
Code Style Guides | [6 empty] | 5 |  | 5 | 0.83333
Wiki Structure + Maintenance | [6 empty] | 5 |  | 5 | 0.83333
Project Proposal + Contract | [6 empty] | 20 | 30 | 50 | 8.3333
MRs + IRs | [7 empty] | 30 | 30 | 5
Tutor Weekly Meetings | [7 empty] | 72 | 72 | 12
Internal Weekly Meetings | [7 empty] | 72 | 72 | 12
Total | 75 | 223 | 93 | 112 | 428 | 135 | 52 | 204 | 894 | 149
p.P. | 12.5 | 37.1667 | 15.5 | 18.6667 | 71.3333 | 22.5 | 8.6667 | 34 | 149

## LVA Estimation
Vorbesprechung: 1 Stunde
Vorbereitung auf den Einstiegstest: 1 Stunde
Einstiegstest: 4 Stunden
Kickoff-Treffen: 1 Stunde
12x Treffen mit Tutor: 12 Stunden
3x Management Review: 3 Stunden
Vorbereitung auf Präsentationen (Management Review, ASE Day): 3 Stunden
Gruppeninterne Treffen/ Meetings, Projektmanagement: 30 Stunden
Ideenfindung, Projektvorschlag, Projektauftrag: 5 Stunden
Einarbeitung in die Technologien: 10 Stunden
Implementierung: 60 Stunden
Qualitätssicherung / Testen: 18 Stunden
ASE-Day: 2 Stunden